## Pineapple
Project Risks
Impact | Probability (P) | Rating | Previous | Initial | Reference | Title | Description & Impact Statement | Business Impact | Risk Response | Mitigation Plan Description | Decision date dd-month-yy | Estimated cost | Provision for budget | Responsible | Target (Plan) dd-month-yy | Done (Do) dd-month-yy | Result (Check,Act) dd-month-yy | Project Name | Imported On
1 | 23.0% | Low (0.92) |  |  | 2.1 | 2.1 | Project DR4 schedule slip Time to Market slippage | 1 | Adapt Project Schedule | Mitigation:Quicken finalizing the Projec Scope and set the Projec DR4 Last chance corrective action: | 2019-10-31 |  |  |  | 2019-10-31 | 1970-01-01 | 1970-01-01 | Pineapple | 2020-03-24 12:38
2 | 50.0% | Low (4.0) | 2 |  | 2.2 | Highland – Build-2 shipment delay | AOS CD schedule slip; as least option, review and adapt the schedule |  | revise CD Schedule revise CD Schedule | Mitigation:Strictly follow and check Build-2/3 Acceptance Criteria Monitor progress closely, dig out risks and implement actions in time | 1970-01-01 |  |  |  | 1970-01-01 | 2019-10-25 | 2019-10-25 | Pineapple | 2020-03-24 12:38
3 | 70.0% | Moderate (8.4) |  | 1 | 2,3 | 2Highland – proto units BOMs delay | Decision making on Build-2 units price delay PO/GL issuance delay |  | revise CD Schedule | Mitigation:Get BOMs ready in Agile 2 wks prior to Shipment date | [7 empty] | Pineapple | 2020-03-24 12:38
1 | 60.0% | Low (2.4) |  |  | 2,4 | Highland – Build-3 shipment delay | Schedule slip |  |  | Mitigation:Strictly follow and check Build-2/3 Acceptance Criteria Monitor progress closely, dig out risks and implement actions in time | [7 empty] | Pineapple | 2020-03-24 12:38
2 | 50.0% | Low (4.0) |  |  | 2,5 | P1 Process for SQA build | Quality of proto units to SQA & Country Specific SCC |  | revise System Test and CSC schedule. Secure Budget to replacce required number of proto units | Mitigation:Do all the necessary HW & HQA Testing guaranteeing Respin avoidance Inspect all TRs for accuracy and completeness Improve P1 Process |  |  |  |  | 2019-10-25 |  |  | Pineapple | 2020-03-24 12:38
3 |  |  |  |  | 3,1 | HW & SW resources critical | Product viability, provisionnning level |  |  | Mitigation:adapt provisionning Last chance corrective action:more resources, cost growth |  |  |  |  | 2019-10-25 | 2019-10-25 | 2019-10-25 | Pineapple | 2020-03-24 12:38