## Pineapple
Project Risks
Impact | Probability (P) | Rating | Previous | Initial | Reference | Title | Description & Impact Statement | Business Impact | Risk Response | Mitigation Plan Description | Decision date dd-month-yy | Estimated cost | Provision for budget | Responsible | Target (Plan) dd-month-yy | Done (Do) dd-month-yy | Result (Check,Act) dd-month-yy | Project Name | Imported On
4 | 70.0% | Low (1.0) | 1 | 1 | 1.1 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | Low (2.0) | 1 | 1 | 1.2 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | Low (3.0) | 1 | 1 | 1.3 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | Low (4.0) | 1 | 1 | 1.4 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | Moderate (6.0) | 1 | 1 | 1.5 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | Moderate (7.0) | 1 | 1 | 1.6 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | Moderate (9.0) | 1 | 1 | 1.7 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | Moderate (10.0) | 1 | 1 | 1.8 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14
4 | 70.0% | High (11.5) | 1 | 1 | 1.9 | Many products in parallel | Overloaded Metiers | Business impact indeed | FAst response, Sonic style | Mitigation:Priority on content\nLast chance corrective action:Delay product availability or some major content | 2020-12-15 | 1000ME | 2000ME | Iksanov | 2020-12-15 | 2020-12-15 | 2020-12-15 | Pineapple | 2020-04-23 23:14