## Sheet0
Registry Type | Unique ID | Title | State | Priority | Owner | Optional Information | Due Date | Detailed Description | Status Updates and Resolution Description | Created Date | Closed Date | Related Risks
Action | 1719 | DR1 presented to Asad | Closed | Medium | Vijay; Surajit; Edgard | AI from DR1, assigned by Asad |  | DR1 presented to Asad on 10/11/19. Other attendees - Chuck; Raymond; Paul; Edgard; Surajit; Kashif | Asad provided Conditional Approval | 13-ноя-2019 | 13-ноя-2019 | 2.5,2.3,2.1
Action | 1720 | Improve OS6860N-P48Z procurement cost at least by 5% at DR4 | Active | Medium | Dickson | AI from DR1, assigned by Asad | 30-мар-2020 | Improve OS6860N-P48Z procurement cost at least by 5% at DR4 time to get 65% margin at 70% discount. AI from DR1 | 1 | 13-ноя-2019
Action | 1721 | Improve OS6860N-U28 procurement cost at least by 5% at DR4 | Active | Medium | Dickson | AI from DR1, assigned by Asad | 30-мар-2020 | Improve OS6860N-U28 procurement cost at least by 5% at DR4 time to get 65% margin at 70% discount. Action Item from DR1 |  | 13-ноя-2019
Action | 1722 | at DR4 time to get 65% margin at 70% discount Dickson Mar 15 2020 Need Field Plan to introduce OS6860N-U28 | Active | Medium | Akshat | AI from DR1, assigned by Asad | 15-мар-2020 | Need Field Plan to introduce OS6860N-U28 since we donâ??t have replacement for 6860E-U28 at $8100 list |  | 13-ноя-2019
Action | 1723 | Improve OS6860N-P48M procurement cost at least by 5% at DR4 | Active | Medium | Dickson | AI from DR1, assigned by Asad | 30-мар-2020 | Improve OS6860N-P48M procurement cost at least by 5% at DR4 time to get 65% margin at 70% discount. Action Item from DR1 |  | 13-ноя-2019
Action | 1724 | Look at higher list pricing â?? 5% increase | Active | Medium | Akshat | AI from DR1, assigned by Asad | 15-мар-2020 | Look at higher list pricing â?? 5% increase |  | 13-ноя-2019
Action | 1725 | Improve OS6900-X48C4E procurement cost at least by 5% at DR4 | Active | Medium | Dickson | AI from DR1, assigned by Asad | 15-мар-2020 | Improve OS6900-X48C4E procurement cost at least by 5% at DR4 time to get 65% margin at 70% discount |  | 13-ноя-2019
Action | 1726 | Must get Broadscan agreement for Trident3 signed by BRCM asap | Active | Medium | Akshat; Dickson; Ron Baldwin | AI from DR1 | 20-ноя-2019 | Must get Broadscan agreement for Trident3 signed by BRCM asap |  | 13-ноя-2019
Action | 1727 | Refine SW Dev Plan and ST Plan, | Active | High | Anil; Don | AI from DR1 - assigned by Asad | 20-ноя-2019 | Refine SW Dev Plan and ST Plan, each 1 week atleast, to accomplish DR4 NOT later than 03/31/20 Suggestion: Plan new Code Drop (CD-2) delivering OS6860N Uplink Modules by 01/10/20. Since 8.6 R2 DR4 is moved to 12/15/19 & since 8.7 R1 Scope Change, finalizing revised Dev plan is moved to 11/20/19. |  | 14-ноя-2019
Decision | 1728 | P1 Process â?? make sure all the necessary HW/HQA Testing complete preventing 100% respin after SQA build | Closed | High | Raymond; Paul |  |  | P1 Process â?? make sure all the necessary HW/HQA Testing complete and inspect all Test Reports to ensure completeness and compliance to the defined acceptance criteria and 100% respin prevention |  | 14-ноя-2019 | 14-ноя-2019
Action | 1729 | Pilot build has to complete before March end | Active | Medium | Raymond |  | 15-мар-2020 | Pilot build has to complete before March end |  | 14-ноя-2019