## 9000 SERIES SIP
Project Risks
Impact | Probability (P) | Rating | Previous | Initial | Reference | Title | Description & Impact Statement | Business Impact | Risk Response | Mitigation Plan Description | Decision date dd-month-yy | Estimated cost | Provision for budget | Responsible | Target (Plan) dd-month-yy | Done (Do) dd-month-yy | Result (Check,Act) dd-month-yy | Project Name | Imported On
5 |  | Moderate (10.0) |  |  | 1.1 | November availability | The new phones range could not be sold by end of the year 2019 as expected | TBD DR3 | Avoid | Need to add necessary resources and budget to ensure november DR4 | 2019-01-25 |  |  | PCT | -1 | -1 | -1 | 9000 SERIES SIP | 2020-05-28 20:43
5 |  | Low (5.0) |  |  | 2.1 | Negotiation with Sercomm still ongoing | Budget needed for the project could be increased |  | Mitigate | Contingency reserve | 2019-01-25 |  |  | J. Tang | 2019-06-30 |  |  | 9000 SERIES SIP | 2020-05-28 20:43
5 |  | High (20.0) |  |  | 3.1 | Contractual Budget | Financing the NRE SIP Budget 230 Kâ?¬ = 270 KUSD NRE current around 600 KUSD Gap to Project budget: 330KUSD | ??? | Mitigate | Purchasing continue to negotiate molds and certification costs (too high ) Mitigation could be to accept a mechanism of amortization to absorb part of the gap (jeff Tang ) | 2019-01-25 |  |  | R. Bai, J. Peterle | 2019-03-31 | 2019-03-07 | 2019-05-15 | 9000 SERIES SIP | 2020-05-28 20:43
5 |  | Moderate (10.0) |  |  | 3.2 | Super Wide Band management | ALE identifies a risk on SERCOMM compliance and obligation to fulfill SWB requirements due to DSPG and/or SIP limitation/technical issues. | ??? | Mitigate | ALEâ??s team to support SERCOMM in the design and demand to DSPG | 2019-01-25 |  | 2MY | PCT | 2019-05-03 | 2019-10-25 | 2019-12-18 | 9000 SERIES SIP | 2020-05-28 20:43
4 |  | High (12.0) |  |  | 3.3 | Product target costs fulfillment | Risk on product cost target achievement at DR4: Sercomm is committed to work on a Cost Reduction plan but is not committed on result as of DR1 | ??? | Mitigate | Re options to further re-assess/challenge PRD to target cost and further challenge Sercomm on their components suppliersâ?? baseline, in a Design-to-cost approach | 2019-01-25 |  |  | R. Bai | 2019-03-31 | 2019-03-29 | 2019-05-15 | 9000 SERIES SIP | 2020-05-28 20:43
3 |  | Moderate (9.0) |  |  | 3.4 | Sales Volumes | Risk on product cost: quoted product costs are only valid for volumes provided in Business plan. Lower volumes may impact product cost. |  | Avoid | Ensure volumes figures are accurate | 2019-01-25 |  |  | D. Zhou | 2019-03-31 | 2019-03-29 | 2019-05-15 | 9000 SERIES SIP | 2020-05-28 20:43
3 |  | High (12.0) |  |  | 3.5 | LINUX OS Software | Risk on Project cost : high price increase likely to occur after end of 2020 on Wind River development licenses | 60Kâ?¬/year | Mitigate | ALE to investigate alternate Linux distribution to Wind River for 9000 Series, such as Yocto distribution | 2019-01-25 |  |  | F. Li | 2019-03-31 | 2019-03-31 | 2019-03-31 | 9000 SERIES SIP | 2020-05-28 20:43
4 |  | Moderate (8.0) |  |  | 3.6 | Statement of Work | Legal SOW ready to be signed Production and IP access and transfer at no cost under agreed conditions |  | Mitigate | Targeted date of SOW ready for signature or under final discussion at DR1 | 2019-01-25 |  |  | R. Bai | 2019-03-08 | 2019-03-08 | 2019-04-30 | 9000 SERIES SIP | 2020-05-28 20:43
3 |  | Moderate (6.0) |  |  | 4.1 | Target landed costs very challenging | More expensive phones in mass production |  | Transfer | ODM to Sercomm to get lower landed costs | 2019-01-25 |  |  | PCT | 2019-05-03 |  |  | 9000 SERIES SIP | 2020-05-28 20:43
4 |  | Moderate (8.0) |  |  | 4.2 | Existing SW resources is not enough to cover 9000 requirements Project deliverable is highly depending on the hiring status | Delay project schedule (How much delay depending on the resoucre gap) |  | Mitigate | More resources from other projects to fill the gap Overtime working | 2019-01-25 |  |  | F. Li | 2019-03-29 |  |  | 9000 SERIES SIP | 2020-05-28 20:43
5 |  | Low (5.0) |  |  | 4.3 | SWB technical feasability is yes according to NOE phone experience. But SWB on SIP Phone is the first try with DVF9919, even on DSPG side. Chipset performance issue is foreseen as a potential risk, raised by DSPG | SWB cannot be delivered on 9000 series |  | Accept | Agreed by PLM to remove SWB in case it really happens | 2019-01-25 |  |  | F. Li ; D. Zhou | 2019-04-12 | 2019-10-25 | 2019-12-27 | 9000 SERIES SIP | 2020-05-28 20:43
2 |  | Moderate (6.4) |  |  | 4.4 | Customisation: Removable L Shape grid could introduce vibration, to be double confirmed on the prototypes | BP/end users cannot customize by themselves |  | Mitigate | A manufacture changeable solution is managed in parallel as plan B | 2019-01-25 |  |  | F. Li | 2019-03-29 | 2019-10-25 | 2019-12-27 | 9000 SERIES SIP | 2020-05-28 20:43
3 |  | Moderate (6.0) |  |  | 4.5 | USB Addon: USB Addon are not existing yet. Therefore it won`t be possible to do EMC/EMS tests with the Addons connected to the phone. We could have surprises when addon will be developped, such as an EMC/EMS issue with the phone | BP/end users cannot use addon. Or impact on cost because phone layout is requested after product is released |  | Mitigate | Mitigation = mockup of an addon + a serial to USB converter Avoid = Addon will be in the project | 2019-01-25 |  |  | F. Li | 2019-03-22 | 2019-10-25 | 2019-12-27 | 9000 SERIES SIP | 2020-05-28 20:43
2 |  | Low (2.0) |  |  | 4.6 | ODM provider does not have rich experience on IP phone design. Technical mistakes may be done during development phasis | Lower the product quality or delay the schedule |  | Mitigate | 1. Based on Sercomm tests, ALE HW shanghai qualification tests (meaning the kind of test not done by QA people, but relevant for healthy HW) 2. All Sercomm design source files are shared with ALE. So that ALE can continue the design anytime we decide | 2019-01-25 |  |  | F. Li ; D. Zhou | 2019-04-26 | 2019-10-25 | 2019-12-27 | 9000 SERIES SIP | 2020-05-28 20:43
2 |  | Low (4.0) |  |  | 4.7 | customization: holes in the L Shape grid could modify the speaker response and impact audio signal | Lower the product quality or delay the schedule to fine tune |  | Mitigate | Measure as soon as possible the audio response with a grid. Possibility to mockup with 3D printer several grids to find the best one for audio. | 2019-01-25 |  |  | F. Li ; D. Zhou | 2019-05-17 | 2019-10-25 | 2019-12-27 | 9000 SERIES SIP | 2020-05-28 20:43
3 |  | Moderate (6.0) |  |  | 4.8 | Display: We didn`t see the display proposed by sercomm. We could have surprise on the perception in real in terms of contrast and color | Lower the product quality or delay the schedule and impact the cost |  | Mitigate | See as soon as possible the display quality and decide if OK or not. | 2019-01-25 |  |  | F. Li ; D. Zhou | 2019-03-15 | 2019-10-25 | 2019-12-27 | 9000 SERIES SIP | 2020-05-28 20:43
3 |  | Moderate (6.0) |  |  | 5.1 | Not enough TS resources for the support (lab tests, Beta support) | Not enoug resources to organize efficient BETA support or internal testing (knowing the support is priority for TS TEC and not launching) |  | Mitigation | - Validation done by R&D Tx with different 3rd party systems - Organize a survey in a defined period (example: 1 month) and no more a BETA test phase with few identified partners | 2019-01-25 |  |  | V. Stoll |  |  |  | 9000 SERIES SIP | 2020-05-28 20:43
4 |  | Moderate (8.0) |  |  | 5.2 | No agreement from BPS managing 3rd party systems for 9000 series Beta test participation | No 9000 series beta phase with 3rd party systems (late bugs discovering on the field) |  | Mitigation | - Organize a survey, with BP doing himself some tests on 3rd party client(s) site(s), or doing the direct support of his end users. In a defined limited period of time (1 month ?) with few TX samples. - If no 3rd party system at all available for Beta-Test, then backup with SIP Wise Rainbow solution (internal ALE Tests + external tests with OXO OXE Beta partners). - Manage 3rd party systems suggested by OXO Beta partners managing 3rd party systems : R&D white list supported systems ? - Beta-Test with OXE SIP Business. - R&D / Validation tests with supported 3rd party system(s) must guarantee 9000 Series quality and interoperability. | 2019-01-25 |  |  | V. Stoll |  |  |  | 9000 SERIES SIP | 2020-05-28 20:43
4 |  | Moderate (8.0) |  |  | 5.3 | No possibility to remote trace efficiently 9000 Series installed on 3rd party systems / Serviceability missing. | No possibility to investigate correctly the TX issues (TS / R&D) |  | Mitigation | - Mission to the Beta site (TS/R&D) to investigate on site the TX issues = cost + human resource consumption. - Lessons learned : to develop after TR/DR4 the missing serviceability | 2019-01-25 |  |  | V. Stoll |  |  |  | 9000 SERIES SIP | 2020-05-28 20:43
3 |  | Low (3.0) |  |  | 5.4 | Beta-Test in holidays period | - Beta-Test bad efficiency as Beta partners not available. - No TS TEC Support. |  | Mitigation | - Avoid organizing Beta-Test in holidays periods (i.e Christmas holidays : all German partners not available for 3 weeks). - To redefine the planning. | 2019-01-25 |  |  | V. Stoll |  |  |  | 9000 SERIES SIP | 2020-05-28 20:43
4 |  | High (12.0) |  |  | 5.5 | Beta-Test duration too short. | - Not enough time to get end users feedbacks. - Issues observed after TR. - Known issues (R&D Validation, Beta sites) not solved before TR. - Too many Major and Minor issues at TR. |  | Mitigation | - Increase Beta-Test duration. - Restrictions on features not mature at TR. - Quality Criteria based on TS proposal : 5 ECMA max at CI - 3 ECMA max at TR. - R&D managing and solving CRs in high priority. | 2019-01-25 |  |  | V. Stoll |  |  |  | 9000 SERIES SIP | 2020-05-28 20:43
4 |  | Moderate (8.0) |  |  | 5.6 | Super Wide Band (OPUS) audio quality not at good level at CI/TR/DR4. | - Super Wide Band not ready in time. - Super Wide band quality not correct for Beta and / or TR/DR4. |  | Mitigation | - descope feature in case Super Wide Band is not in a good quality. - redefine the planning in order to solve Super Wide Band audio issues. | 2019-01-25 |  |  | V. Stoll |  |  |  | 9000 SERIES SIP | 2020-05-28 20:43